## Gantt Chart w % Complete
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
| Create the Client class | 2020-02-22 | 22 | 2020-02-29 | 7 | 0 | 7 | TBD | 0
| Create the Pokemon class and database | 2020-02-22 | 22 | 2020-02-29 | 7 | 0 | 7 | TBD | 0
| Create the Grid class | 2020-02-22 | 22 | 2020-02-29 | 7 | 0 | 7 | TBD | 0
| Create the Interface | 2020-02-22 | 22 | 2020-02-29 | 7 | 0 | 7 | TBD | 0
| Create Server | 2020-02-22 | 22 | 2020-02-29 | 7 | 0 | 7 | TBD | 0
| Implement interface and testing movement on grid | 2020-03-01 | 1 | 2020-03-07 | 6 | 0 | 6 | TBD | 0
| First client-server interaction test | 2020-03-07 | 7 | 2020-03-14 | 7 | 0 | 7 | TBD | 0
| Implement client-server calls | 2020-03-15 | 15 | 2020-03-21 | 6 | 0 | 6 | TBD | 0
| First playtest | 2020-03-22 | 22 | 2020-03-28 | 6 | 0 | 6 | TBD | 0
| Additional network interactions | 2020-03-29 | 29 | 2020-04-04 | 6 | 0 | 6 | TBD | 0
| Improve encounter interface | 2020-04-05 | 5 | 2020-04-11 | 6 | 0 | 6 | TBD | 0
| Add multiple users feature | 2020-04-12 | 12 | 2020-04-18 | 6 | 0 | 6 | TBD | 0
| Continue Development | 2020-04-19 | 19 | 2020-04-25 | 6 | 0 | 6 | TBD | 0
| Polish game and finishing touches | 2020-04-26 | 26 | 2020-05-08 | 12 | 0 | 12 | TBD | 0

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 3 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 3 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 5 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 5 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 3 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 7 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 4 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 1 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 4 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 3 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 3 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 9 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 5 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 6 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 1 | Rachel | 0%

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 3 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 5 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 4 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 3 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 3 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 5 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 9 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 3 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 5 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 5 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 4 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 5 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 3 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 5 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 4 | Rachel | 40%