## Sheet1
WEEK | START DATE | TASK NAME | Notes | Group Member's Role
1 | 2020-02-04 | Flesh out project design |  | TBD
2 | 2020-02-11 | Emulate a grid with location data |  | TBD
3 | 2020-02-18 | Create interface, visualize movement on grid |  | TBD
4 | 2020-02-25 | Create creature database, continue interface work | Minimal database data required | TBD
5 | 2020-03-03 | First client-server interaction test | Minimal encounter visuals required | TBD
6 | 2020-03-10 | Implement necessary client-server calls for playtest |  | TBD
7 | 2020-03-17 | First playtest, tie up loose ends/fix errors |  | TBD
8 | 2020-03-24 | Add aditional network interactions | Database should be finished | TBD
9 | 2020-03-31 | Spring Break
10 | 2020-04-07 | Flesh out encounter interface |  | TBD
11 | 2020-04-14 | Continued Development |  | TBD
12 | 2020-04-21 | Add support for multiple users on the same game | This includes multiple network interactions | TBD
13 | 2020-04-28 | Continue work of previous week |  | TBD
14 | 2020-05-05 | Polishing/Final Touches |  | TBD
15 | 2020-05-12 | Finals Week